## Sprint 1
Status | Task | Assigned To | Deliverable | Time Estimated to Complete | Time Spent | Time Remaining (at end of sprint) | Over/Under | Support Required | Notes
Complete | use case diagram | Shakil Islam | Done | 1 hours
| architecthure | Shakil Islam | Done | 1 hours
| home page layout | Shakil Islam | Done | 3 hours
| Database | Rakib Al Hasan | done | 4 hours
| Solar Calculator | Shakil Islam | done | 2 hours
| Product management | Anjuman Ara | done | 4 hours
| Login Interphase | Arnob paul | done | 2 hours
Incomplete
Partially Complete
Summary of hours:
[5 empty] | 6 hour | Shakil Islam
[5 empty] | 2 hour | Arnob Paul
[5 empty] | 3 hour | Rakib Al Hasan
[5 empty] | 4 hour | Anjuman Ara